## Action Items
Action Item Tracking Table
Action Item # | Priority | Action Required | Source | Date Opened | Status | Assigned To | Date Assigned | Date Due | Date Closed | Progress Update/ Resolution
1 |  | Create Monthly GTA Achievements List | Bobbie send to Angela | 2016-09-09 | Closed | Angela Addison | 2016-09-09 | each Month |  | James Fullerton - Angela's backup / Send to Shea / link to recognition
2 |  | New Slogan | Maria and Jim | 2016-09-12 | Closed | Grace | 2016-09-09 |  | 2016-09-12 | Helping taxpayers get it right, to keep Florida’s future bright.
3 |  | New Picture |  | 2016-09-09 | Closed | Shea | 2016-09-09 |  | 2016-09-16
4 |  | Calendar |  | 2016-09-09 | Closed | Shea | 2016-09-09 |  | 2016-09-12
5 |  | Calendar items |  | 2016-09-09 | Closed | Angela Addison | 2016-09-09 |  |  | Need to add items
6 |  | CPM Article |  | 2016-09-09 | Closed | Bobbie | 2016-09-09 |  | 2016-09-12 | Send final version to Shea / Link to Spotlight on / Send photos to Shea
7 |  | A document with GTA portion of accomplishments / Monthly version |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  | 2016-09-12
8 |  | Description: Business Processes |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  | 2016-09-12 | Business processes are defined and aligned based on workflow, core functions and essential activities. Employees may work in multiple business processes in delivering direct value to our customers and stakeholders.
9 |  | Description: Organizational Processes |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  | 2016-09-12 | Organizational processes are aligned based on traditional reporting structure. Employees in a particular organizational process may perform functions that fall within multiple business processes.
10 |  | Description: Operational Support Processes |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  | 2016-09-12 | Operational support processes help underpin core functions by providing program-wide guidance, essential assistance and key coordination among the operational and organizational processes.
11 |  | Description: Solution Support |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  | 2016-09-12 | Solution Support Services helps minimize user down time by providing timely technical support to all GTA employees. GTA users can submit requests for technical assistance, training or implementation support for any computer, mobile device, miscellaneous accessory (e.g., monitor), peripheral device (e.g., printer), software or network issue. Solution Support Services coordinates the escalation of issues to the Information Services Program (ISP) when needed.
12 |  | Description: Workforce |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  | 2016-09-12 | The Workforce Transition team provides SUNTAX and other operational systems support and training, business process technical support, and develops and delivers operational communications. Users may submit inquiries or requests for assistance directly to Workforce Transition or through designated individuals according to their business process directives.
13 |  | Description: Work Request |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  | 2016-09-12 | The Work Request Management System (WRMS) provides GTA with a structure to track and manage all technology projects. Authorized users can submit requests for GTA operational systems enhancements, systems maintenance and reporting. Operational systems include SUNTAX, IMS, File and Pay websites and other electronic filing of returns, refund requests, and account information updates.
14 |  | Tax Coordinators |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  |  | Find out which coordinator supports each tax.
15 |  | Interpretors |  | 2016-09-09 | Closed | Grace | 2016-09-09 |  |  | Locate an employee who can translate a foreign language to assist with a taxpayer.
16 |  | Spotlight On, Key Communications, Accomplishments - Need a link to previous articles as they change |  | 2016-09-09 | Closed | Shea/Gail | 2016-09-09 |  |  | Concept - Main Article on larger side of the page with links to archived items to the right. Key Communications and Accomplishments ready.
17 |  | Create Accomplishments page with place for photos |  | 2016-09-16 | Closed | Shea | 2016-09-16 |  |  | Long term action item
18 |  | Vision and Mission description |  | 2016-09-16 | Closed | Grace | 2016-09-16 |  |  | Read GTA’s vision and mission statements.
19 |  | Stategic Initiative description |  | 2016-09-16 | Closed | Grace | 2016-09-16 |  |  | See, at-a-glance, GTA’s strategic focus for the fiscal year.
20 |  | Performance Measures description |  | 2016-09-16 | Closed | Grace | 2016-09-16 |  |  | Review our performance measures.
21 |  | Program Training |  | 2016-09-16 | Closed | Bobbie | 2016-09-16 |  |  | Find tax law course materials and a schedule of upcoming classes.
22 |  | Revenue Law Library |  | 2016-09-16 | Closed |  | 2016-09-16 |  | 2016-09-16 | REMOVE
23 |  | Sunrise |  | 2016-09-16 | Closed | Bobbie | 2016-09-16 |  |  | Access by authorized users to search deposit information, images, and reports.
24 |  | Report out of Date Content with form to input information |  | 2016-09-16 | Closed | Shea | 2016-09-16 |  |  | Fix title / no description
25 |  | Report a Problem with Intranet Links with form |  | 2016-09-16 | Closed | Shea/Gail | 2016-09-16 |  |  | no description
26 |  | Provide Maria with language for processes |  | 2016-09-23 | Closed | Nancy | 2016-09-23
27 |  | Update language for processes |  | 2016-09-23 | Closed | Maria | 2016-09-23
28 |  | Rename processes and update language |  | 2016-09-23 | Closed | Shea | 2016-09-23
29 |  | Draft org chart & Validate |  | 2016-09-23 | Closed | Grace | 2016-09-23
30 |  | Draft Overview of processed for landing page |  | 2016-09-23 | Closed | Grace | 2016-09-23
31 |  | Explore ways to make is easier to read text |  | 2016-09-23 | Closed | Shea | 2016-09-23
32 |  | Remove Central Operations in leadership page view |  | 2016-09-23 | Closed | Gail | 2016-09-23
33 |  | Modify Leadership page to match Org Chart | Email from Grace | 2016-09-28 | Closed | Shea | 2016-09-28
34 |  | Make Org Charts Interactive pages instead of PDF | Email from Shea | 2016-09-28 | Closed | Shea | 2016-09-28
35 |  | Learn More for processes - create additional text
36 |  | Issue Identified: Screen resolution or font size making some text (Leadership) wrap | Meeting | 2016-10-11 | Closed | Shea | 2016-10-11
37 |  | Issue Identified: Some menu options not viewable due to screen resolution / Explore supermenus where text goes down instead of across | Meeting | 2016-10-11 | Closed | Shea | 2016-10-11
38 |  | See: Montana for navigation to reduce scrolling | Meeting | 2016-10-11 | Closed | Shea | 2016-10-11
39 | 1 | Design page for Second Level - Use Picture (smaller than main page), Camera with information, Use Purpose and Goals from PAMS, quick links to side, Link to sub-processes to side and others as needed. Use white background, blue text. See Example Links - About Us (Strategies, initiatives, etc) , Contacts, Procedurres, Reports, Team Site, Resources (Or external links to other sites - may want in a global area) | Meeting | 2016-10-11 | Closed | Shea | 2016-10-11 | 2016-10-21
40 | 1 | Design page for Third Level - No picture | Meeting | 2016-10-11 | Closed | Shea | 2016-10-11 | 2016-10-21
41 | 1 | Goals / Purpose for each process area | Meeting | 2016-10-14 | Closed | Angela Addison | 2016-10-14 | 2016-10-21
42 | 1 | Activities / Purpose for third level | Meeting | 2016-10-14 | Closed | Bobbie / Jan | 2016-10-14 | 2016-10-21 |  | Resource Mgmt and BTO not complete - will need to write
43 |  | Request from Manny - Development of the Tableau Dashboards page | Email | 2016-10-27 | Closed | Grace | 2016-10-27
44 |  | Discuss - Convert PAM page from Excel to Tableau dashboard | Email | 2016-10-27 | Closed | Grace | 2016-10-27
45 | 1 | Edit first level Purposes | Meeting | 2016-10-28 | Closed | Bobbie / Jan | 2016-10-28 | 2016-10-04
46 | 1 | Pictures for second level | Meeting | 2016-10-28 | Closed | Gail/Angela | 2016-10-28
47 | 1 | Spotlight on for NOV will SCORE | Meeting | 2016-10-28 | Closed | Grace | 2016-10-28
48 |  | December - Photo contest for main page / Need release | Meeting | 2016-10-28 | Closed | Grace | 2016-10-28
49 | 1 | Meeting with Manny | Meeting | 2016-10-28 | Closed | Nancy | 2016-10-28 |  | 2016-10-28
50 | 1 | Taxpayer Education Page - Need content | Meeting | 2016-10-28 | Closed | All | 2016-10-28 |  |  | Need purpose and activities
51 | 2 | Get Suresh on PDF of PAMs | Meeting with Manny | 2016-11-04 | Closed | Ladaysha | 2016-11-04 |  |  | Link PAM Summary Intranet - PDF or Link to dashboard based on access. Need Suresh to create PDF
52 | 3 | Build All Dashboards Portal and link on GTA HOME page - Deliver via SharePoint in a Portal/Dashboard | Meeting with Manny | 2016-11-04 | Closed | Manny | 2016-11-04
Note on A2: Sequential number beginning with 1.
Note on C2: The specific action to be performed.
Note on D2: Full Name, Document, Meeting, Discussion, etc.
Note on E2: MM/DD/YYYY
Note on F2: Open or Closed
Note on G2: Full Name
Note on H2: MM/DD/YYYY
Note on I2: MM/DD/YYYY
Note on J2: MM/DD/YYYY
Note on K2: This field should be updated as the action item progresses. The final resolution must be recorded.

## Discussions items
Discussion Item Tracking Table
Action Item # | Discussion Items | Source | Date Opened | Status | Assigned To | Date Closed | Progress Update/ Resolution
1 | Remove the word "processes" from the three processes and just have the following labels: Business, Organizarional, Operational Support. Also add a header label "Processes" above the three processes. | Shea suggestion to Grace emailed on 9/26/16 | 2016-09-26 | Open | Team |  | Pending team review
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Note on A2: Sequential number beginning with 1.
Note on B2: The item or suggestion for discussion
Note on C2: Full Name, Document, Meeting, Discussion, etc.
Note on D2: MM/DD/YYYY
Note on E2: Open or Closed
Note on F2: Full Name
Note on G2: MM/DD/YYYY
Note on H2: This field should be updated as the action item progresses. The final resolution must be recorded.

## Intranet - Current Links top
Links across Top | Pages | Sub pages | Comments
General Tax Administration | Main GTA landing page |  | Need new design / Standard template
Processes | Processes: Account Management | Account Creation
Account Updates
| Processes: Compliance Determination | Lead Development
Audit
Campaigns
Criminal Investigations
| Processes: Receivables Management | Collection
Enforcement
| Processes: Return & Revenue Processing | Check Processing
Data Capture
Document Processing
EFT Processing
Return Reconciliation
| Processes: Taxpayer Aid | Taxpayer Assistance
| Processes: Refunds and Distributions | Accounting Services
Refund Determination
Refund Accounting
Processes: Taxpayer Services
Resource Management | Resource Management: Compliance Standards | Resource Contacts
Case Processing and Review
Compliance Standards Team Site
Workforce Transition
| Resource Management: Financial Management | Financial Management Team Site
Business Technology | Resource Management: Planning & Performance Measures | Leadership Development and Powerpoint Presentations
Planning & Performance Measures Team Site
| Resource Management: Program Development and Support | Legislative Concepts
Resource Management: Resource Management Team Site
Resource Management: GTA Survey Results
Business Technology: Roles by Position
Business Technology: Security
| Business Technology: Technology Management | Initiatives
Work Requests
Business Technology: GTA Systems Suport
Business Technology: Data Suport Services
Business Technology: Mobile Resources
Training | Business Technology: Project Management Office
Business Technology: Zip Code Table
Field Ops | Business Technology: Business Technology Office Team Site
Revenue+A2A1:A29B3A2:A29 | Business Technology: GTA Dashboards
| Training: Program Training | Audit Training System
Class Policy
Course List
Course Material Updates
CPE Credit
Refund Verification Training
Resources
Test Policy
Training Forms
Recorded Training Sessions
Training: Workforce Transition
Field Ops
Revenue: Child Support Enforcement
Revenue: Executive
Revenue: Human Resources
Revenue: Information Services
Revenue: Property Tax
Revenue: RevenueU

## Intranet - Current Side bar
Links side bar | Pages | Sub pages | Comments
Leadership
Vision and Mission
Tax Coordinators
Disaster Information
Helpful Links | BAMS History
GTA Portal
MOBIUS
Revenue Law Library
Sunrise
Interpreters
Need Technical Support?
Work Request
Site Contents

## Main Menu
Main Menu bar
General Tax Administration | Operational | Organizational | Support | Revenue
/sites/gta/Pages/default.aspx | New | New | New | http://dorweb/

## Picture
Picture Area | Language
Picture | (Shea) Need a new picture - Florida / text for location
General Tax Administration (Centered)
Slogan (Centered) | Helping taxpayers get it right, to keep Florida’s future bright.

## GTA Highlights
GTA Highlights
Upcoming Events | Key Communications | Leadership | Spotlight On | Recognition | Delete section header / Make smaller | GTA Highlights
Find upcoming events of interest to you. | Read GTA's monthly Key Communication. | View GTA's leadership team and read their bios. | Read about the Certified Public Manager program | Learn about GTA's accomplishment. |  | communications to keep you up to date
Calendar of GTA events | Maria's monthly key communication | GTA's organization and leadership | A showcase of special areas of interest and achievements within the GTA program / includes new hires or promotions - this description will change with each update | Focus on GTA reported accomplishments
Use a calendar to show events | Link to current key communication | Link to the leadership view with pictures | Link to a monthly spotlight document | Link to GTA version (need to create) document from the Governor's recognition document
(Shea) Need calendar - Done |  |  | (Grace and Bobbie) Need an article on CMP - done | (Grace) need a document with GTA portion of accomplishments / Monthly version
(Angela) Need events - recurring mailouts, letters. Etc. |  |  | Need a link to previous articles as they change | (Grace) establish schedule for recurring updates
(Grace) establish schedule for recurring updates

## Processes
Business Processes | Organizational Processes | Operational Support Processes
Business processes are defined and aligned based on workflow, core functions and essential activities. Employees may work in multiple business processes in delivering direct value to our customers and stakeholders. | Organizational processes are aligned based on traditional reporting structure. Employees in a particular organizational process may perform functions that fall within multiple business processes. | Operational support processes help underpin core functions by providing program-wide guidance, essential assistance and key coordination among the operational and organizational processes.
Learn More - link to more content on the process - for now link to current page for all | Learn More - link to more content on the process - for now link to current page for all | Learn More - link to more content on the process - for now link to current page for all
https://dorsp13.fdor.dor.state.fl.us/sites/gta/Pages/default.aspx | https://dorsp13.fdor.dor.state.fl.us/sites/gta/Pages/default.aspx | https://dorsp13.fdor.dor.state.fl.us/sites/gta/Pages/default.aspx

## Operational
Operational
Subsite | Current Link | Level 3 | Current Link | Level 4 | Current Link | Level 5 | Current Link
Account Management | /sites/gta/process/am/Pages/default.aspx | Account Creation | /sites/gta/process/am/creation/Pages/default.aspx
|  | Account Updates | /sites/gta/process/am/demographics/Pages/default.aspx
|  | Financial Data Update | /sites/gta/process/am/fdu/Pages/default.aspx
|  | Team Site | /sites/gta/process/am/ts/SitePages/Home.aspx
Compliance Determination | /sites/gta/process/cd/Pages/default.aspx | Audit | /sites/gta/process/cd/audit/Pages/default.aspx | Audit Documentation | /sites/gta/process/cd/audit/doc/_layouts/15/start.aspx#/SitePages/Home.aspx
|  |  |  | Audit Team Site | /sites/gta/process/cd/audit/ts/_layouts/15/start.aspx#/SitePages/Home.aspx
|  | Campaigns | /sites/gta/process/cd/campaigns/Pages/default.aspx | Campaigns Team Site | /sites/gta/process/cd/campaigns/TS/SitePages/Home.aspx
|  | Criminal Investigations | /sites/gta/process/cd/investigation/Pages/default.aspx | Criminal Investigations Team Site | /sites/gta/process/cd/investigation/ts/SitePages/Home.aspx
|  | Lead Development | /sites/gta/process/cd/ld/Pages/default.aspx | Lead Development Team Site | /sites/gta/process/cd/ld/ts/SitePages/Home.aspx
|  |  |  | SunVISN Project | /sites/gta/process/cd/ld/sunvisn/SitePages/Home.aspx
|  |  |  | Tax Violations and Rewards Program | /sites/gta/process/cd/ld/Rewards/Pages/default.aspx | Tax Violations and Rewards Team Site | /sites/gta/process/cd/ld/Rewards/Rewards and Tax Violations Team Site/SitePages/Home.aspx
Receivables Management | /sites/gta/process/recievables/Pages/default.aspx | Collection | /sites/gta/process/recievables/collection/Pages/default.aspx
|  | Enforcement | /sites/gta/process/recievables/enforcement/Pages/default.aspx
Refunds and Distributions | /sites/gta/process/refdist/Pages/default.aspx | Account Services | /sites/gta/process/refdist/AccountingServices/Pages/default.aspx
|  | Refund Determination | /sites/gta/process/refdist/refund/Pages/default.aspx
|  | Revenue Accounting | /sites/gta/process/refdist/revenue_accounting/Pages/default.aspx | Intergovernmental Data-Sharing | /sites/gta/process/refdist/revenue_accounting/intergovdatasharing/Pages/default.aspx
|  |  |  | Vouching Unit | /sites/gta/process/refdist/revenue_accounting/vouching/Pages/default.aspx
Return & Revenue Processing | /sites/gta/process/returnprocess/Pages/default.aspx | Check Processing | /sites/gta/process/returnprocess/check/Pages/default.aspx | Image Cash Letter Project | /sites/gta/process/returnprocess/check/imagecashletter/Pages/default.aspx
|  | Data Capture | /sites/gta/process/returnprocess/datacapture/Pages/default.aspx
|  | Document Processing | /sites/gta/process/returnprocess/docprocess/Pages/default.aspx
|  | EFT Processing | /sites/gta/process/returnprocess/eft/Pages/default.aspx
|  | Return Reconciliation | /sites/gta/process/returnprocess/returnrec/Pages/default.aspx | Filing Compliance Verification | /sites/gta/process/returnprocess/returnrec/filingcomp/Pages/default.aspx
|  |  |  | Returned Items | /sites/gta/process/returnprocess/returnrec/returneditems/Pages/default.aspx
|  |  |  | TAMS | /sites/gta/process/returnprocess/returnrec/tams/Pages/default.aspx
Taxpayer Aid | /sites/gta/process/aid/Pages/default.aspx | Taxpayer Assistance | /sites/gta/process/aid/assistance/Pages/default.aspx

## Organizational
Organizational
Subsite | Current link | Level 3 | Current Link | Level 4 | Current Link | Level 5 | Current Link | Level 6 | Current Link
Taxpayer Services - (Moved from Processes) | /sites/gta/process/TSP/Pages/default.aspx | Team Site | /sites/gta/process/TSP/ts/_layouts/15/start.aspx#/SitePages/Home.aspx
|  | TSP - Rewards and Recognition | /sites/gta/process/TSP/TSPRR/Pages/default.aspx
Field Operations | /sites/gta/offices/Pages/default.aspx | Service Centers | /sites/gta/offices/SC/Pages/default.aspx | Subsite for each Service Center | Too Numberous to list | Audit - Ex Alachua Audit | Too Numberous to list | Team Site | Too Numberous to list
|  | Service Centers (Map) |  |  |  | Collections - Ex Alachua Collections | Too Numberous to list | Team Site | Too Numberous to list
[6 empty] | OR Team Site - Ex Pittsburh | Too Numberous to list

## Support
Support
Subsite | Current Link | Level 3 | Current Link | Level 4 | Current Link | Level 5 | Current Link | Level 6 | Current Link
Business Technology | /sites/gta/tech/Pages/default.aspx | Business Technology Team Site | /sites/gta/tech/TS/SitePages/Home.aspx | NA | NA
|  | Contract Management | /sites/gta/tech/conmgmt/default.aspx | Team Site | /sites/gta/tech/conmgmt/TS/SitePages/Home.aspx
|  | Data Support services | /sites/gta/tech/dss/default.aspx | Team Site | /sites/gta/tech/dss/TS/SitePages/Home.aspx
|  | e-Services | /sites/gta/tech/esvcs/SitePages/Home.aspx | Team Site | /sites/gta/tech/esvcs/TS/SitePages/Home.aspx
|  | GTA Dashboards | /sites/gta/tech/dash/Pages/default.aspx | NA | NA
|  | GTA Systems Support | /sites/gta/tech/gss/default.aspx | Acct Mgmt & Rec Mgmt Team Site | /sites/gta/tech/gss/amrmTS/SitePages/Home.aspx
|  |  |  | Case Management Team Site | /sites/gta/tech/gss/cmTS/SitePages/Home.aspx
|  |  |  | GSS Team Site | /sites/gta/tech/gss/TS/SitePages/Home.aspx
|  |  |  | Payment & Fund Distribution Team Stie | /sites/gta/tech/gss/pfdTS/SitePages/Home.aspx
|  |  |  | Rev Proc & Ret Rec Team Site | /sites/gta/tech/gss/rprrTS/SitePages/Home.aspx
|  | Mobile Resources | /sites/gta/tech/mobileresources/Pages/default.aspx | NA | NA
|  | One-Stop Registration | /sites/gta/tech/OneStop/Pages/default.aspx | One-Stop Project Site | /sites/gta/tech/OneStop/OneStopTS/SitePages/Home.aspx
|  | Project Management Office | /sites/gta/tech/PMO/SitePages/Home.aspx | NA | NA
|  | Strategic Initiative Facilition | /sites/gta/tech/StratInit/Pages/default.aspx | NA | NA
|  | SUNTAX | /sites/gta/tech/suntax/Pages/default.aspx | NA | NA
|  | Technology Management - (Can Delete once Initiatives - Lead Development and Solution Support are moved) | /sites/gta/tech/mgmt/Pages/default.aspx | Initiatives - (Can delete once Lead Development is moved) | /sites/gta/tech/mgmt/projects/Pages/default.aspx | Lead Development- (Need to move this to Projects at some point) | /sites/gta/tech/mgmt/projects/leaddev/SitePages/Home.aspx
|  | Solution Support - (Moved from under BTO - Technology Mgmt) | /sites/gta/tech/mgmt/support/Pages/default.aspx
Resource Management | /sites/gta/rm/Pages/default.aspx | Compliance Standards | /sites/gta/rm/polproc/Pages/default.aspx | Case Processing and Review | /sites/gta/rm/polproc/caseProc/Pages/default.aspx | Case Processing and Review Team Site | /sites/gta/rm/polproc/caseProc/TS/SitePages/Home.aspx
|  |  |  | Compliance Standards Team Site | /sites/gta/rm/polproc/TS/SitePages/Home.aspx
[6 empty] | Workforce Transition Team Site | /sites/gta/rm/polproc/wft/wftTS/SitePages/Home.aspx
|  |  |  | Training - (I think we can delete this site once Program Training is moved under Compliance Determination; however, need to moveClass-Schedule page to progtrain) | /sites/gta/train/Pages/default.aspx | Program Training - (Organizationally under RMP - Compliance Standards) | /sites/gta/train/progtrain/Pages/default.aspx | Computer Audit Analyst | /sites/gta/train/progtrain/caa/Pages/default.aspx
[8 empty] | Course List | /sites/gta/train/progtrain/CourseList/Pages/default.aspx
[8 empty] | Refund Verification Training | /sites/gta/train/progtrain/refundverification/Pages/default.aspx
[8 empty] | Resources | /sites/gta/train/progtrain/Resources/Pages/default.aspx
[8 empty] | Tax Audit Supervisor | sites/gta/train/progtrain/tas/Pages/default.aspx
|  | Financial Management | /sites/gta/rm/fm/Pages/default.aspx | Financial Management Team Site | /sites/gta/rm/fm/TS/SitePages/Home.aspx | UT SUNTAX Billing | /sites/gta/rm/fm/TS/UTSUNTAXBilling/SitePages/Home.aspx
|  |  |  | RT Related Contract Management | /sites/gta/rm/fm/rtConMgmt/_layouts/15/start.aspx#/SitePages/Home.aspx
|  | Planning and Performance Measures | /sites/gta/rm/planning/Pages/default.aspx | Planning and Performance Measures Team Site | /sites/gta/rm/planning/TS/SitePages/Home.aspx
|  | Program Development and Support | /sites/gta/rm/prgmdev/Pages/default.aspx | Legislative Concepts | /sites/gta/rm/prgmdev/rmplegcon/Pages/default.aspx
|  |  |  | Program Development and Support Team Site | /sites/gta/rm/prgmdev/TS/SitePages/Home.aspx
|  | Resource Management Team Site | /sites/gta/rm/TS/SitePages/Home.aspx
|  | Taxpayer Education and Communication - (Hidden - New Site) | /sites/gta/rm/tec/Pages/default.aspx | TEC Team Site | /sites/gta/rm/tec/ts/_layouts/15/start.aspx#/SitePages/Home.aspx
|  |  |  | SharePoint | /sites/gta/rm/tec/SP/Pages/default.aspx | Team Site | /sites/gta/rm/tec/SP/TS/SitePages/Home.aspx | Management Update - (Shea - Can we delete?) | /sites/gta/rm/tec/SP/TS/Management%20Update/default.aspx
|  | Workforce Transition (Moved from Compliance Standards) | /sites/gta/rm/polproc/wft/Pages/default.aspx | FAQ's | /sites/gta/rm/polproc/wft/FAQs/Pages/default.aspx
Work Requests - (Moved from BTO - Technology Mgmt) | /sites/gta/tech/mgmt/workrequest/SitePages/Work%20Request%20Dashboard.aspx | Projects | /sites/gta/tech/mgmt/workrequest/projects/SitePages/Home.aspx | Large Projects | /sites/gta/tech/mgmt/workrequest/projects/lge/SitePages/Home.aspx
|  |  |  | Recurring Projects | /sites/gta/tech/mgmt/workrequest/projects/recur/SitePages/Home.aspx
|  |  |  | Small Projects | /sites/gta/tech/mgmt/workrequest/projects/sm/SitePages/Home.aspx

## Resources
Resources
Resources | Description | Current Link | Technology | Description | Current Link | Quick Links | Description | Current Link
Vision and Mission | Read GTA's vision and mission statements. | /sites/gta/Pages/Vision-and-Mission.aspx | Solution Support | (Shea draft to Grace) Need language for Solution Support, Workforce and Work Request - Done | /sites/gta/tech/mgmt/support/Pages/default.aspx | GTA Portal | Access by authorized users to SUNTAX BI Reports, Tableau reports, and GTA Work Request Management System. | http://dor-wpap003.dor.dcs.sdc.state.fl.us:50000/irj/portal
Strategic Initiatives | See, at-a-glance, GTA’s strategic focus for the fiscal year | (Angela) document summary / https://dorsp13.fdor.dor.state.fl.us/sites/gta/rm/Documents/GTA_Strategic_Initiatives_Graphic.pdf Strategic Initiatives…same place because that is where the last two copies of the strategic initiatives were located. | Workforce |  | /sites/gta/rm/polproc/wft/Pages/default.aspx | MOBIUS | Access financial tax data previously housed in the legacy Mainframe Database. | http://dorweb/gta/mobius/
Performance Measures | Review our performance measures | (Angela) Link on Frank's page https://dorsp13.fdor.dor.state.fl.us/sites/gta/rm/_layouts/15/WopiFrame.aspx?sourcedoc=/sites/gta/rm/Documents/GTA_PAMs.xlsx&action=default PAMs…it is under Resource management because they wanted it linked from the resource management page under the performance measures header. | Work Request |  | /sites/gta/tech/mgmt/workrequest/SitePages/Work%20Request%20Dashboard.aspx | Program Training | Find tax law course materials and a schedule of upcoming classes | /sites/gta/train/progtrain/Pages/default.aspx
Tax Coordinators | Find out which coordinator supports each tax | /sites/gta/rm/prgmdev/rmplegcon/Lists/Tax Coordinators/AllItems.aspx |  |  |  | Revenue Law Library |  | http://dorlaw.fdor.dor.state.fl.us/Pages/Home.aspx
Interpreters | Locate an employee who can translate a foreign language to assist with a taxpayer | /sites/gta/Pages/Interpreters.aspx |  |  |  | Sunrise | Access by authorized users to search deposit information, images, and reports | http://sunrise:7778/SunRise/Logon.act
[6 empty] | Suntax Roles by Position | Find SUNTAX roles mapped to position numbers. Review the roles assigned to a position before submitting an IS-600010, SUNTAX Security Authorization Change Request Form. | http://dorweb/gta/st/security/role_definitions.html

## Footer
Footer
Contact SharePoint Team to report a problem
Survey | Leave off for now
Report out of date content | (Shea) Need an email group | Gail, Angela, Shea
Report a Problem with Intranet links | (Shea) Need an email group | Gail, Angela, Shea

## Misc
Site Name | Current Link | Level 3 | Current Link
GTA BI - (Hidden - Shea, is this in use?) | /sites/gta/bi/Pages/Default.aspx
GTA Program Staff - (Hidden - Not in Use) | /sites/gta/exe/Pages/default.aspx | Process Owners - (Hiddent - In Use) | /sites/gta/exe/procown/SitePages/Home.aspx